## Slide 1
To our Workfront customers,
Use this PPT as a starting point when creating your own training for the new Workfront experience—to get existing users up to date on the changes or to onboard new employees.
Replace the standard images with screenshots from your Workfront instance, customize the steps, add information specific to your organization, etc.
Then send the file to your users (we recommend PDF format, for easier viewing) or use the PPT to teach a live class.
Your Workfront Customer Enablement team
Provide feedback about this template to cxlearningprograms@workfront.com

## Slide 2
Planner: Getting started
Project managers, power users, project creators, and more

## Slide 3: Create a new (blank) project.

## Slide 4
1
From the Main Menu (blank project).
Select the Main Menu and click Projects.
Once the Projects page opens, click the +New Project drop-down menu and select New Project.
A blank project is created.
Name your project, fill in the project details, add tasks and assignments, timelines, etc. to your new project.
2
3
4
Go to the Main Menu to get started with all Workfront objects; this replaces the Classic Global Navigation bar.

## Slide 5: Create a new project from a template.

## Slide 6
1
From a pre-defined project template.
Select the Main Menu and click Projects.
Once the Projects page opens, click the +New Project drop-down menu and select the desired template from the New from Template menu.
A pre-defined template project pop-up menu is generated.
Fill in the Create Project from Template details and click Save Changes to save your new project. Once saved, update your project tasks, assignments, etc.
2
3
4
Go to the Main Menu to get started with all Workfront objects; this replaces the Classic Global Navigation bar.

## Slide 7: Convert a request into a new project.

## Slide 8: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
1
From a request (converted to a project).
Find the request in the Requests area.
  Note: Your organization may be using a dashboard to manage requests.
Open the request by clicking its name.
From the request More menu, select Convert to Project.
Select to create a new blank project or create from template.
Fill out the pop-up menu and click Save Changes to create the project.
2
3
4
5
Go to the Main Menu to get started with all Workfront objects; this replaces the Classic Global Navigation bar.

## Slide 9: The most important project fields.

## Slide 10: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Top 12 Project Fields.
Every organization has its own requirements for which project detail fields must be filled in when a project is created.
Workfront recommends focusing on 12 specific fields to speed up project creation. When these fields are filled in properly, reporting on projects is more accurate and complete.
Although some fields are filled in via the project template, others need to be completed at the time of project creation.
Follow your organization’s naming convention for project names.
Don’t forget to set a date for your project to start or complete (depending on your selection in the Start From menu).
Leave the project status in Planning while making changes to the timeline.

## Slide 11: Top 12 fields for quick and easy project creation.
For detailed information about these 12 fields , refer to The most important project details guide.
1. | Name | 7. | Resource Manager
2. | Description | 8. | Group
3. | Schedule From | 9. | Schedule
4. | Status | 10. | Resource Pools
5. | Project Owner | 11. | Access to the Project for Viewers/ Contributors
6. | Project Sponsor | 12. | Custom Forms

## Slide 12: Find a project.

## Slide 13: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
On a Dashboard.
Find your dashboard in the My Dashboards list or Shared with Me list.
Click the dashboard name to open it.
Find the report that lists your projects.
Click the project name to open it.
Use the Main Menu to navigate to the Dashboards area.
Pin a dashboard to make it quick and easy to access.
1
2
3
4

## Slide 14: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
In the Projects area.
Use the Filter option to narrow down your project list.
  My Projects—Status of Current and your name in the project team.
  Projects I Own—Your name in the Project Owner field. Any Status.
  Projects I’m On—You’re assigned a task; created the project; or your name in the Project Sponsor or Project Owner field.
Click the project name to open it.
Use the Main Menu to navigate to the Projects area.
Change the View to see different columns of information about the projects in the list.
1
Pin projects that you want to access frequently, so you can get to them quickly.
2

## Slide 15: Plan a project.

## Slide 16: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
From a Template – 5 Step Overview.
The project template provides a starting point for your project, with tasks already created, suggested timelines, etc. Then you can adjust tasks, assignments, and the timeline.
Focus first on these five fields:
  Task name
  Assignments
  Duration
  Planned Hours
  Predecessors
Leave the project status in Planning while making changes to prevent assignment notifications until setup is complete.
1
2
3
4
5

## Slide 17: Plan a project: Tasks.

## Slide 18: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Project tasks.
The Tasks list established by the project template can be changed to suit the needs of your specific project.
Add tasks using the Insert Above/Insert Below options.
Duplicate tasks, if needed.
Delete unneeded tasks.
Organize tasks into a parent-child (task-subtask) structure, as needed.
Adjust the order of tasks with a drag and drop.
1
Click on the More menu to open additional task functions (see below for details).
More menu selections (from above).
2
3

## Slide 19: Tips and tricks.
Start task names with a verb (approve, create, edit, etc.), so it’s clear what work needs to be done.
A clear, concise task description ensures the user knows everything important about the assignment.
Add a “project summary” task at the top of the project. This is a parent task that all subsequent tasks roll up to that gives you information like total project duration and planned hours (this is helpful for larger projects).
Attach related documents to applicable tasks (or the project itself).

## Slide 20: Plan a project: Assignments.

## Slide 21: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Assignments based on job role.
It’s recommended that project templates have tasks assigned to job roles, to serve as placeholders until actual people are assigned.
Double-click into the Assignments field.
Hover so a list of users with that job role appears.
Select a user from the list.
This method of assigning work doesn’t guarantee the person is available during the time the work should be completed.
A warning icon indicates if a person has time out of the office (marked in their Workfront time-off calendar) during the duration of the task. Selecting this user could affect the project timeline.
1
2
3

## Slide 22: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Assignments based on availability.
Select Scheduling from the left panel.
Set the date range for making assignments.
Drag and drop tasks from the Unassigned area to an available person.
Enter duration, planned hours, and predecessors on tasks before using the scheduling timeline. This ensures tasks show up on the right dates and for the right amount of time.
Click the arrow next to a task name to expand the box for more information.
To see recommended task assignments based on availability, click the Auto button.
Make bulk assignments by job role with the Actions options.
Adjust what you see in the timeline through the settings.
1
2
3

## Slide 23: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Assignments by name.
If you know who the task should be assigned to you, enter their name directly in the project.
Double-click into the Assignments field.
Type the person’s name into the field.
Select a user from the list.
Assigning someone by name doesn’t guarantee the person is available during the time the work should be completed.
1
2
3
You may assign multiple people to a single task.

## Slide 24: Tips and tricks.
Wait to assign people to tasks until after you’ve established duration and predecessors. This way, you can make sure you’re assigning someone who is available during that time period.
Parent tasks shouldn’t be assigned to users/roles. This affects estimates in Workfront’s resource scheduling and planning tools.

## Slide 25: Plan a project: Duration.

## Slide 26: Duration.
The “window of opportunity” for completing a task.
The difference between the planned start date and the planned completion date of the task.
Example: When the duration of a task is 5 days, the task needs to be completed during that 5-day period. It doesn’t necessarily mean the task will take 5 full days to complete. The final day of the duration is the task deadline/due date.
For more information about task duration, refer to the knowledge base article Understanding Task Duration and Duration Type.

## Slide 27: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Project Duration.
Double-click into the Duration field to activate the in-line editing.
Enter the task duration in full-day increments (such as 5d or 1d). Click out of the field to save.
The planned start date and completion dates of the task change automatically.
Duration is typically set on tasks from the project template, so you can update durations, as needed. You need to add duration to tasks you create.
The duration of a parent task is, generally, the total of the subtasks’ durations. You cannot edit the parent task’s duration.
Clicking in the start on or due on columns to set a date also sets a task constraint. Task constraints affect the ability of planned start and completion dates to change automatically. Learn more here.
Planning status prevents due date notifications while changing durations
1
2
3

## Slide 28: Tips and tricks.
Enter duration in whole day increments. Avoid using partial days.
Duration can be affected when assignees mark their time out of the office using Workfront’s time-off calendar. Check the project setting “User Time Off” to see if it’s set to consider or ignore the time-off calendar.
Duration is required for accurate information in Workfront’s resource planning and scheduling tools.

## Slide 29: Plan a project: Planned hours.

## Slide 30: Planned hours.
The amount of time estimated/required for the assigned users to complete the work.
Planned hours are intended to happen during the task duration.
Example: A task has 8 planned hours but a 5-day duration. This means it’s estimated the actual work will take 8 hours. But those 8 hours can happen any time during that 5-day period. The final day of the duration is the task deadline/due date.
For more information about task planned hours, refer to the knowledge base article Understanding Planned Hours.

## Slide 31: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Planned hours.
Double-click into the Planned Hours field to activate the in-line editing.
Enter the amount of time needed/estimated to complete the work. Click out of the field to save.
The planned hours do not affect the planned start date and completion dates of the task.
Planned hours are typically set from the project template. You can update planned hours, as needed. You need to add hours to tasks you create.
The planned hours on a parent task are the total planned for all the child tasks. You cannot change the planned hours on a parent task.
1
2

## Slide 32: Tips and tricks.
Planned hours are required for accurate information in Workfront’s resource planning and scheduling tools.
Planned hours can be entered in minutes (m), hours (h), days (d), weeks (w), or months (mo). Parent tasks always display the planned hours in hours.

## Slide 33: Plan a project: Predecessors.

## Slide 34: Predecessors.
A task that another task (successor or dependent task) depends on.
Predecessors help sequence the tasks in the project, so they occur in the proper order.
Example: A task called Write Copy is the predecessor to a task called Create Layout. This means the work on the layout should not begin until the copy is written.
For more information about task predecessors, refer to the knowledge base article Understanding Predecessors.

## Slide 35: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Predecessors.
Double-click into the Predecessors field to activate the in-line editing.
Enter the number of the task (the predecessor) that should be completed before this task (the successor or dependent).
Hit Return/Enter to lock in the change, then click out of the field to save.
You should see the planned start date and planned completion date of the task change automatically.
1
2
Planning status prevents due date notifications while changing durations
If the dates don’t change on the task when you enter predecessors, there might be a task constraint applied to the task. Learn more here.

## Slide 36: Tips and tricks.
Use the “chain” feature to quickly set up predecessors.
Set task constraints to “as soon as possible” if scheduling the project from a start date. Set task constraints to “as late as possible” if scheduling from a completion date.
(Workfront recommends using Start Date with “as soon as possible” constraint for optimal use.)

## Slide 37: Take a project live.

## Slide 38: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Planning to Live.
Check the project and timeline to ensure everything is as desired.
Change the Status of the project from Planning to Current.
Once the project is in Current status, notifications go out to the task assignees. Current may not be the “active” status of choice for your organization; be sure to identify the appropriate selection for your projects.
You may also change the Status in the project details.
1
2
Ensure all job role assignments have been switched to individual users or teams. Otherwise, assignees will not be notified and the work may not get done.

## Slide 39: Adjust live timelines.

## Slide 40: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Adjusting timelines.
Use durations and predecessors to adjust dates. Avoid selecting dates, as this changes the constraint and breaks the predecessor relationships.
Double-click into the Duration field to activate the in-line editing.
Change the amount of duration, then click out of the field to save the changes. The dates update automatically.
1
2
Clicking in the start on or due on columns to set a date also sets a task constraint. Task constraints affect the ability of planned start and completion dates to change automatically. Learn more here.

## Slide 41: Close a project.

## Slide 42: Project completion checklist.
Make sure all tasks and issues are marked as Complete (or an equivalent status).
Attach relevant documents.
Log final hours and review previously logged hours for accuracy.
Make final updates.
Make sure outstanding task and issue approvals have been resolved or canceled (open issues or approvals will prevent you from closing out the project).

## Slide 43: Workfront Home.
Sed ut perspiciatis unde omnis iste natus error sit voluptatem accusantium doloremque laudantium, totam rem aperiam, eaque ipsa quae ab illo.
Live to Closed.
Finally, change the project status to Complete.
All tasks must be 100% complete in order to close the project and mark it as complete. Complete may not be the “closed” status of choice for your organization; be sure to identify the appropriate selection for your projects.
You may also change the Status in the project details.
1

## Slide 44: Tips and tricks.

## Slide 45
When someone tags you in an update, it sends an in-app notification. Access these from your colored and numbered notification icon (to the left of the Main Menu).
While creating and setting up a new project, make sure the project status is set to Planning. This prevents notifications from going out while changes to assignments and the timeline are made.
Use Favorites and pins to “bookmark” items—these are your best friends when it comes to finding things quickly.

## Slide 46: Thank you.